## test of tool
Total Factors | 132
Planning Factors | 15.4
Implementation Factors | 16.6
Delivery Factors | 32.6667
Management Factors | 14.4
Grade | 79.1
The novopay project has a grade 79.1 out of 132
|  | Factor | Delivery Factors
|  | Issues | Deployment Testing | 7 | Integration of Software | 7 | Technology Tools | 3 | Trouble Shooting | 10
|  | Mitigation | Unit Test Plan |  | Integration Test Plan |  | System Test Plan |  | Acceptance Test Plan
|  | Test coverage |  | 80% |  | 50% |  | 10% |  | 60%
|  | Factor | Implementation Factors
|  | Issues | Project Monitoring | 6 | Schedules/Deadlines | 6 | Scope Creep | 5 | Workflow Communication | 14
|  | Mitigation | Administrative Tasks Plan |  | Critical Path Analysis |  | Adjustment Plan |  | Communication Plan
|  | Initial |  | 1 |  | 1 |  | 0.5 |  | 0.6
|  | Final |  | 0.2 |  | 0.4 |  | 0.5 |  | 0.3
|  | Factor | Management Factors
|  | Issues | Contract Status | 10 | Management Assumptions | 11 | Project Expertise | 5 | Project Management Skills | 5 | Stakeholder Politics | 12
|  | Communicate | Progress |  | Risk |  | Team |  | Management |  | Deliverable
|  | Frequent meetings |  | 1 |  | 0 |  | 0 |  | 1 |  | 1
|  | Direct Communication |  | 1 |  | 1 |  | 1 |  | 0 |  | 1
|  | Glossary of progress |  | 1 |  | 1 |  | 0 |  | 0 |  | 1
|  | Factor | Planning Factors
|  | Issues | Project Complexity | 6 | Project Objectives and Goals | 11 | Project Risk Analysis | 14
|  | Mitigation | Systems thinking |  | Goals and Methods Matrix |  | Risk Analysis
|  | Requirement Analysis |  | 0.7 |  | 0 |  | 1
|  | System Design |  | 0.7 |  | 0 |  | 0
|  | Architectural Design |  | 0.7 |  | 1 |  | 1
|  | Module Design |  | 1 |  | 0 |  | 0
Use Novopay project to test tool
Deployment Testing : Test coverage 80%. Ref1 'Some important areas of functionality were not fully tested prior to Go Live'
Integration of Software: Test coverage 50%. Ref11 'It was evident before Go Live that many schools did not understand and were not ready for the changes to their roles. Some schools were also not prepared from a technological perspective, and found the move to an online system challenging'
Technology Tools : Test coverage 10% Ref16 'The online form tracking system had not been made available to schools, so they could not tell which requests had been actioned.'
Trouble Shooting : Test coverage 60% Ref21 'A number of transactions could not be performed online either by design or due to defects of various sorts, requiring users to enter data manually onto forms and send them to the Service'
Project Monitoring: Initial:1 Final: 0.2 Ref32 'As a consequence of its involvement with the Project Board and efforts to get the project over the line, SSC was not able to exercise its monitoring role properly, as it had lost its detachment.'
Schedules/Deadlines: Initial:1 Final: 0.4 Ref34 'Over the course of the project, Talent2 had missed agreed milestones or deadlines, which eroded trust and confidence in its ability to deliver. '
Scope Creep: Initial:0.5 Final: 0.5 Ref41 'Work commenced on the requirements for the schools payroll project in October 2008. This process was lengthy, and was never actually completed. Even after Go Live, new requirements were being discovered'
Workflow Communication: Initial:0.6 Final:0.4 Ref47, Ref48, Ref49
Contract Status: Ref64 'While there were contractual levers available, the lack of a range of sanctions made it difficult for the Ministry to apply them. The lack of clarity around performance obligations created by the 40 contractual documents further affected the Ministry’s ability to manage Talent2’s performance'
project expertise: Ref87 'Neither the Ministry nor Talent2 demonstrated the level of capability required to plan, manage and execute effective testing. As a consequence of requirements definition, early testing was wasted. It was on the introduction of Absurdity that testing practices began to meet the expected level of good practice.'
Project Complexity: Ref115 'Requirements definition, design, development and testing activity were all occurring in parallel, making it very difficult to maintain a known level of quality. '
Project Objectives and Goals : Ref123 'Long-duration projects will rarely meet the expectations established at their inception'
Project Risk Analysis: Ref134,Ref135,Ref136,Ref137,Ref138